## Dashboard
🚀 REFLEXKERNEL-ALIGNED AUTONOMIC SENSOR PLATFORM TRACKER
Hardware Layer for ReflexKernel v0.1+ ¦ Created: June 07, 2026 ¦ "Saddle Intelligences" Vision
PROJECT VISION & ALIGNMENT
Goal: Build the physical/hardware autonomic nervous system layer that feeds ReflexKernel (or equivalent software embodiment system). This hardware provides real-world Perception (tactile, motion, audio, biometrics, environment) and Output/Actuation (physical expression of reflexes). Long-term: The full system (hardware + ReflexKernel) becomes a "saddle" — a grounded body that higher Intelligences (LLMs, agents, eventually custom AIs) can interface with, teach, and inhabit. Key ReflexKernel mappings: FSRs + MPU6050 + Mic → fast reflexes (flinch, orient, tension, freeze). Biometrics → affective state. Vibration/LEDs/Servo → physical expression of VirtualBody. Phased build: Start with high-signal Perception sensors → Add affective biometrics → Add Output actuators → Integrate with ReflexKernel software layer.
KEY MILESTONES (ReflexKernel Integration Focus)
ID | Milestone | Success Criteria (ReflexKernel-aligned) | Status | Target Date | Actual | Notes
M1 | Core Perception Online | FSR array + MPU6050 + Mic reading cleanly into structured JSON on ESP32/Pi | To Do
M2 | First Reflex Mapping | Real sensor events trigger appropriate reflex primitives in simulation (flinch on sudden pressure/sound) | To Do
M3 | Affective Layer Added | MAX30102 + GSR feeding arousal/valence estimates into Thought/Emotion Bridge | To Do
M4 | Physical Output Working | Vibration motors + LEDs expressing reflexes (flinch = vibration burst, tension = LED intensity) | To Do
M5 | ReflexKernel Integration Start | Hardware data flowing into ReflexKernel Perception layer (or compatible interface) | To Do
M6 | Teaching Loop Closed | Higher intelligence (Python agent or local LLM) can send seeds/rewards and see hardware respond | To Do
M7 | Portable Node | Battery-powered wearable/sensor node with wireless data + local logging | To Do
M8 | Full Saddle Prototype | End-to-end: Real sensors → ReflexKernel → Local LLM/agent interface with persistent learning | To Do
PROGRESS
Completed: |  | / 8
Progress:
QUICK REFERENCE - ReflexKernel Layer Mapping
Perception Layer (High Priority): FSR (tactile/contact), MPU6050 (motion/orient), Microphone (sudden sound), DHT22 (context)
Affective / Thought Bridge: MAX30102 (HRV/arousal), GSR (skin conductance)
Output / Actuation Layer: Vibration motors (flinch/tension), NeoPixel LEDs (state expression), Servo (orient/posture)
Core Platform: Raspberry Pi 5 (run ReflexKernel), ESP32 (sensor hub + low-level output)
See 'Testing_Checklist' tab for detailed test procedures aligned to each milestone.

## Shopping_List
🛒 REVISED SHOPPING LIST — ReflexKernel Perception + Output Aligned
Layer colors: Blue = Perception ¦ Orange = Output/Actuation ¦ Green = Core Platform ¦ Yellow = Affective ¦ Update yellow cells as you source.
Priority | Layer | Component | Description / ReflexKernel Value | Qty | Est. Unit $ | Est. Total $ | Source | Status | Actual Unit $ | Actual Total $ | Date Received | Reflex Mapping | Notes / Integration Ideas
1 | Perception | FSR Force Sensitive Resistor (0.5" round) | Primary tactile/contact sensing. High-signal input for flinch & tension reflexes. | 4 | 6 |  | Amazon/Adafruit | To Buy |  |  |  | flinch, tension, contact events | Buy 4 for multi-point array. Voltage divider with 10k resistor.
1 | Perception | MPU6050 6-Axis Accel/Gyro (GY-521) | Motion, sudden movement, orientation. Excellent for orient, freeze, posture context. | 1 | 4 |  | Amazon | To Buy |  |  |  | orient, freeze, motion signature | I2C. Very reliable and cheap.
1 | Perception | Microphone Module (MAX9814 or KY-038) | Detect sudden loud sounds. Critical for believable startle/flinch reflex. | 1 | 5 |  | Amazon | To Buy |  |  |  | flinch (sudden_loud), audio context | MAX9814 preferred (better AGC). Maps directly to startle primitive.
1 | Perception | DHT22 Temp & Humidity Sensor | Environmental + body temperature context. Useful for affective fusion. | 2 | 5 |  | Amazon | To Buy |  |  |  | affective context, environmental state | One near body, one ambient. Easy 1-wire.
2 | Affective | MAX30102 Pulse/HR/SpO2 Module | Heart rate variability as arousal proxy. Strong input for Thought/Emotion Bridge. | 1 | 8 |  | Amazon/AliExpress | To Buy |  |  |  | arousal estimation, affective state | I2C. Use good library (SparkFun/Adafruit).
2 | Affective | GSR / Galvanic Skin Response Module | Skin conductance = emotional arousal/valence signal. Excellent affective modality. | 1 | 8 |  | Seeed/Amazon | To Buy |  |  |  | arousal, valence, emotional intensity | Calibrate baseline. Pairs well with HRV.
2 | Core Platform | Raspberry Pi 5 (4GB or 8GB) | Main brain to run ReflexKernel software layer + data processing. | 1 | 85 |  | Official/reseller | To Buy |  |  |  | Hosts ReflexKernel + saddle interface | Prioritize if budget allows. Run full kernel here.
2 | Core Platform | ESP32 DevKit V1 | Wireless sensor aggregation hub + low-level actuation driver. | 1 | 6 |  | Amazon/AliExpress | To Buy |  |  |  | Sensor fusion + Output driver | WiFi/BT. Bridge between sensors and Pi.
3 | Output | Vibration Motor / Haptic Actuator | Physical expression of flinch, tension, startle. Makes reflexes felt. | 3 | 3 |  | Amazon | To Buy |  |  |  | flinch, tension (physical output) | Drive via MOSFET or motor driver. Map intensity to reflex strength.
3 | Output | NeoPixel / Addressable LED (short strip or ring) | Visual state expression. Color/intensity = arousal, valence, tension level. | 1 | 10 |  | Adafruit/Amazon | To Buy |  |  |  | state visualization, affective expression | Easy to drive from ESP32/Arduino. Very expressive.
3 | Output | SG90 / MG90S Servo (or better) | Physical orientation or posture change. Maps to orient primitive. | 1 | 5 |  | Amazon | To Buy |  |  |  | orient, posture expression | Future Phase 3+. Start with vibration/LEDs first.
4 | Core Platform | Breadboard 400pt + Jumper Wire Kit | Essential prototyping foundation. | 1 | 8 |  | Amazon | To Buy |  |  |  | — | Get good quality wires.
4 | Core Platform | MicroSD Module + 16GB+ Card + RTC DS3231 | Local structured logging (mirrors ReflexKernel StructuredLogger). | 1 | 8 |  | Amazon | To Buy |  |  |  | data persistence, logging | Useful once data pipeline is solid.
4 | Core Platform | LiPo 3.7V Battery + TP4056 Charger | Portable / wearable operation for real-world testing. | 1 | 8 |  | Amazon | To Buy |  |  |  | mobile nodes | Or start with USB power bank.
ESTIMATED TOTALS

## Layer_Mapping_Guide
🗺️ REFLEXKERNEL LAYER MAPPING GUIDE
PERCEPTION LAYER (Hardware → ReflexKernel Input)
Primary Goal: Provide fast, high-signal, real-world stimuli that trigger believable reflexes. Recommended First Sensors: FSR array + MPU6050 + Microphone (highest immediate value for flinch/orient/tension primitives). Data Format Recommendation: Structured JSON per tick or event, e.g.: {"timestamp": "...", "modality": "tactile", "fsr": [12, 45, 8, 67], "mpu": {"ax":.., "ay":.., "gz":..}, "audio_peak": 0.87, "dht_temp": 28.4} This format maps cleanly into ReflexKernel's Sensor abstraction or external input.
OUTPUT / ACTUATION LAYER (ReflexKernel → Hardware Expression)
Goal: Make internal reflex and affective states physically visible/felt. Mapping Examples: - flinch / startle → Short strong vibration burst + LED flash - tension / sustained arousal → Continuous low vibration or rising LED intensity - orient → Servo movement toward stimulus direction + LED direction cue - affective state (high arousal/negative valence) → Red/orange LED color shift Start simple with vibration + LEDs. Add servo later. Create a thin ActuationHub that translates ReflexKernel commands into pin outputs.
AFFECTIVE / THOUGHT-EMOTION BRIDGE
MAX30102 (HRV) + GSR provide continuous affective signals. These feed the Thought/Emotion Bridge layer rather than direct reflex triggers. Useful for longer-term state modulation and higher-intelligence interpretation.
INTEGRATION PATH (Recommended)
Phase 1: ESP32 collects FSR + MPU6050 + Mic → outputs structured JSON over serial/WiFi Phase 2: Raspberry Pi receives data → feeds into ReflexKernel Perception (or simulation bridge) Phase 3: Add MAX30102 + GSR for affective enrichment Phase 4: Add vibration motors + NeoPixels as Output actuators driven from ReflexKernel Phase 5: Close the loop with local LLM/agent sending thought seeds + receiving state + giving rewards/demos

## Budget_Phases
💰 BUDGET TRACKER & REFLEXKERNEL-ALIGNED PHASES
OVERALL BUDGET
Allocated Budget ($): | 180
Est. Total (Shopping_List):
Actual Spent:
Remaining:
PHASED PURCHASING (ReflexKernel Priority)
Phase | Focus | Key Items | Est. Cost | Target | Status | ReflexKernel Goal
Phase 1: Core Perception | High-signal reflexes | FSR x4, MPU6050, Mic, DHT22 x2, Breadboard, ESP32 | 55 | Week 1-2 | To Do | Get tactile + motion + audio into structured data
Phase 2: Platform + Affective | Brain + emotional signals | Raspberry Pi 5, MAX30102, GSR, SD/RTC | 110 | Week 2-3 | To Do | Run ReflexKernel + feed affective data
Phase 3: Physical Output | Make reflexes visible/felt | Vibration motors x3, NeoPixel, basic driver | 25 | Week 3-4 | To Do | Hardware expression of flinch/tension/orient
Phase 4: Integration | Close hardware ↔ software loop | Any missing + servo if needed | 20 | Week 4+ | Future | Full Perception → ReflexKernel → Output pipeline

## Testing_Checklist
🧪 TESTING CHECKLIST — ReflexKernel Aligned Sensor Platform
Use this checklist as you bring up hardware and integrate with ReflexKernel. Update Status column. Yellow cells are editable.
Phase | Test # | Test Name | What to Verify / Success Criteria | Method / Tools | Status | Date Tested | Notes / Results / Log Location
Phase 1: Hardware Validation | 1.1 | FSR Array Basic Test | Each FSR reads analog values cleanly. No noise or stuck readings when pressed. | Arduino/ESP32 analogRead + Serial Plotter or simple Python script | Not Started
Phase 1: Hardware Validation | 1.2 | MPU6050 Motion Test | Accel & gyro values update smoothly. Detects tilt and sudden movement. | I2C scan + example sketch (or library test) | Not Started
Phase 1: Hardware Validation | 1.3 | Microphone Sudden Sound Test | Detects loud sounds with clear peak detection. Low false positives in quiet room. | MAX9814 or KY-038 test sketch + serial output | Not Started
Phase 1: Hardware Validation | 1.4 | DHT22 Environmental Test | Stable temperature & humidity readings. Compares reasonably with room thermometer. | DHT library example + multiple readings over 5 mins | Not Started
Phase 2: Data Pipeline | 2.1 | Structured JSON Output | ESP32/Pi outputs clean, timestamped JSON with all active sensors. | Custom logging script writing to Serial + file | Not Started
Phase 2: Data Pipeline | 2.2 | Wireless Data Transmission | Data reliably reaches Raspberry Pi over WiFi (or serial if wired). | ESP32 WiFi client + simple receiver on Pi | Not Started
Phase 2: Data Pipeline | 2.3 | Data Logging & Persistence | Logs are written to SD card or file with timestamps and survive power cycle. | MicroSD module test + RTC sync check | Not Started
Phase 3: Reflex Mapping | 3.1 | Real Data → Simulation Injection | Real sensor JSON can be fed into ReflexKernel (or simplified version) as stimuli. | Bridge script that converts hardware JSON → ReflexKernel stimulus format | Not Started
Phase 3: Reflex Mapping | 3.2 | Flinch / Startle Reflex Test | Sudden pressure (FSR) or loud sound triggers appropriate flinch + blink + tension in simulation. | Observe Pygame avatar + structured logs in ReflexKernel | Not Started
Phase 3: Reflex Mapping | 3.3 | Orient / Motion Reflex Test | Sudden movement or tilt on MPU6050 triggers orient behavior. | Check reflex trace logs and avatar response | Not Started
Phase 4: Affective Integration | 4.1 | MAX30102 HRV Reading | Clean heart rate and SpO2 values. Reasonable resting HR detected. | Library example + 2-3 minute test on finger | Not Started
Phase 4: Affective Integration | 4.2 | GSR Baseline + Response | Stable baseline at rest. Clear rise in conductance with mild stress/activity. | Simple analog reading + calibration routine | Not Started
Phase 4: Affective Integration | 4.3 | Affective State Fusion | Combined HRV + GSR + other signals produce reasonable arousal estimate. | Simple fusion script or feed into ReflexKernel ThoughtBridge | Not Started
Phase 5: Physical Output | 5.1 | Vibration Motor Test | Motors respond to commands with controllable intensity and duration. | PWM or digital output test from ESP32/Arduino | Not Started
Phase 5: Physical Output | 5.2 | NeoPixel / LED State Expression | LEDs change color/intensity based on simulated reflex or affective state. | Simple state machine driving LEDs from sensor/reflex values | Not Started
Phase 5: Physical Output | 5.3 | Servo Orientation Test | Servo moves in response to orientation or directional stimuli. | Servo library + angle mapping from MPU6050 | Not Started
Phase 6: ReflexKernel Integration | 6.1 | Hardware → ReflexKernel Bridge | Real sensor data flows into ReflexKernel Perception layer (or compatible interface). | Custom adapter / bridge script | Not Started
Phase 6: ReflexKernel Integration | 6.2 | Reflex Firing from Real Stimuli | Real-world events (press FSR hard, clap, sudden move) trigger correct reflexes in ReflexKernel. | Run full ReflexKernel with live data feed + observe avatar + logs | Not Started
Phase 6: ReflexKernel Integration | 6.3 | Teaching Loop Test | Can send thought seeds / rewards from Python and see system respond + learn. | Use ReflexKernel PythonAPI or JSON command interface | Not Started
Phase 6: ReflexKernel Integration | 6.4 | Local LLM / Agent Saddle Test | A local LLM or agent can subscribe to state and send commands/seeds/rewards. | Simple agent script using ReflexKernel interface | Not Started
TESTING PROGRESS SUMMARY
Total Tests: | 20
Passed:
In Progress:
Not Started: