## Dashboard
🚀 TRAVELERS AUTONOMIC SENSOR PLATFORM - BUILD TRACKER
Personal Project Tracker for Bob ¦ Created: June 07, 2026 ¦ "If you cease to learn, you've ceased to live."
PROJECT GOALS
Build a practical, expandable sensor platform inspired by autonomic nervous system / bio-electronics concepts (electronic skin, biogels, stretchable electronics, HRV/GSR monitoring). Core: Arduino + Raspberry Pi hybrid for data collection, processing, and integration with AI agents / Travelers lore (Teller, Ani Void, soul essence sensing, environmental storytelling). Phased approach over ~1 month: Source components → Prototype core → Add biometrics/tactile → Wireless integration → Test & expand into game dev / personal biofeedback. Motivation: Hands-on learning, DIY electrician skills + creative AI/game dev fusion. Keep body tired from work but mind on fire!
KEY MILESTONES CHECKLIST (Update Status column)
ID | Milestone | Description / Success Criteria | Status | Target Date | Actual Date | Notes / Blockers
M1 | Core Platform Setup | Arduino/RPi + breadboard + basic sensor kit assembled and blinking LED test passed | To Do
M2 | Shopping Complete - Phase 1 (Core) | Arduino, breadboard, 37-in-1 kit, wires, ESP32 ordered/received | To Do
M3 | Biometric Sensors Online | MAX30102 (HR/SpO2), GSR, DHT22 reading and logging data | To Do
M4 | Tactile / E-Skin Prototype | FSR pressure sensors + MPU6050 working, basic 'touch' response | To Do
M5 | Wireless Data Transmission | ESP32 sending sensor data to PC / local network / Pi | To Do
M6 | Power & Portability | Battery-powered wearable or portable node tested | To Do
M7 | Integration & Lore Link | Data feeding into simple script / MKDocs / game concept (e.g. Ani sensing) | To Do
M8 | Expansion Planning | List next sensors (EEG-like, more e-skin) and full build docs | To Do
OVERALL PROGRESS
Done Milestones: |  | / 8
Progress %:
QUICK REFERENCE
Previous Shopping List Summary: Arduino Uno or RPi5 + 37-in-1 kit (core) → MAX30102, GSR, DHT22, FSRs, MPU6050, ESP32, batteries, breadboard/jumpers.
Sourcing: Amazon/AliExpress for speed & price; Adafruit/SparkFun for quality/docs. Phased over next month.
Safety (Electrician mode): 5V logic safe, but double-check voltages on sensors. Job site dust/UV - protect components.

## Shopping_List
🛒 SHOPPING LIST & SOURCING TRACKER - Autonomic Sensor Platform
Update Status, Actual Cost, and Notes as you source. Yellow cells = your inputs. Formulas auto-calculate totals.
Priority | Component | Description / Why | Qty | Est. Unit $ | Est. Total $ | Source / Link Notes | Status | Actual Unit $ | Actual Total $ | Date Received | Notes / Substitutions
1 | Arduino Uno R3 (or clone) | Core MCU for sensor reading. Clones fine to start. | 1 | 12 |  | Amazon/AliExpress | To Buy |  |  |  | Start with clone for cost
1 | Raspberry Pi 5 (4GB or 8GB) | For data logging, AI processing, network. Optional but powerful. | 1 | 75 |  | Official or reseller | To Buy |  |  |  | If budget allows; start Arduino first
1 | 37-in-1 Sensor Kit (KEYESTUDIO/ELEGOO) | Best value starter: includes temp, motion, sound, touch, etc. Tutorials included. | 1 | 25 |  | Amazon | To Buy |  |  |  | High priority - gets many basics fast
1 | Breadboard 400pt + Jumper Wires Kit | Essential prototyping. Get good quality wires. | 1 | 8 |  | Amazon/Adafruit | To Buy
2 | MAX30102 Pulse/HR/SpO2 Sensor Module | Heart rate variability & blood oxygen - core autonomic metric. | 1 | 8 |  | Amazon/AliExpress | To Buy |  |  |  | I2C easy
2 | GSR / Galvanic Skin Response Module (Grove or generic) | Skin conductance / sweat / emotional arousal sensing. | 1 | 8 |  | Seeed/Amazon | To Buy |  |  |  | Good for biofeedback
2 | DHT22 Temperature & Humidity Sensor | Accurate body/env temp & humidity. | 2 | 5 |  | Amazon | To Buy |  |  |  | One for body, one for room
2 | FSR Force Sensitive Resistor (0.5" round, Interlink or equiv.) | Pressure/tactile sensing for e-skin prototypes. | 4 | 6 |  | Adafruit/SparkFun/Amazon | To Buy |  |  |  | Buy 4 for multi-point touch
2 | MPU6050 6-Axis Accel/Gyro Module (GY-521) | Motion, posture, vibration sensing. | 1 | 4 |  | Amazon | To Buy |  |  |  | Very cheap, I2C
3 | ESP32 DevKit V1 or similar | WiFi + Bluetooth for wireless data to PC/Pi. | 1 | 6 |  | Amazon/AliExpress | To Buy |  |  |  | Dual core, great value
3 | LiPo Battery 3.7V + TP4056 Charger Module | Portable power for wearable tests. | 1 | 8 |  | Amazon | To Buy |  |  |  | Or use power bank first
3 | MicroSD Card Module + 16GB+ Card | Local data logging on Arduino/Pi. | 1 | 5 |  | Amazon | To Buy
3 | RTC DS3231 Module | Accurate timestamps for logged data. | 1 | 3 |  | Amazon | To Buy
4 | Assorted Resistors, LEDs, Buttons Kit | For testing circuits, indicators, pull-ups. | 1 | 6 |  | Amazon | To Buy
4 | PIR Motion Sensor + HC-SR04 Ultrasonic | Presence and distance for environmental awareness. | 1 | 4 |  | Amazon | To Buy |  |  |  | From kit or separate
5 | Optional: e-Health Shield or MySignals (advanced) | Pre-made biometric shield if you want plug-and-play later. | 0 | 80 |  | Libelium resellers | Future |  |  |  | Nice-to-have, not essential for start
TOTALS

## Budget_Tracker
💰 BUDGET TRACKER & PHASED PURCHASING
OVERALL BUDGET
Total Allocated Budget ($): | 150
Est. Total from Shopping List:
Actual Spent So Far:
Remaining Budget:
PHASED PURCHASING PLAN (Recommended)
Phase | Focus | Key Items | Est. Cost | Target Week | Status | Notes
Phase 1: Foundation | Core MCU + Prototyping Basics | Arduino clone or RPi, 37-in-1 kit, breadboard + wires | 45 | Week 1 | To Do | Get blinking LED + basic sensor read this week!
Phase 2: Autonomic Core | Biometric Sensors | MAX30102, GSR, DHT22 (x2) | 26 | Week 2 | To Do | Focus on HRV + skin response data logging
Phase 3: Touch & Motion | Tactile / E-Skin + Motion | 4x FSR, MPU6050 | 28 | Week 3 | To Do | Build simple pressure array demo
Phase 4: Wireless & Power | Connectivity + Portability | ESP32, LiPo + charger, SD + RTC | 22 | Week 3-4 | To Do | Send data wirelessly, battery test
Phase 5: Polish & Expand | Integration + Future | Any missing, extras, enclosure ideas | 20 | Week 4+ | Future | Tie into Travelers lore / MKDocs

## Build_Phases_Detail
🔧 DETAILED BUILD PHASES & STEP-BY-STEP
PHASE 1: FOUNDATION (Week 1 Goal: Working Arduino + First Sensor Read)
Steps: 1. Unbox Arduino (or Pi) + breadboard. Install Arduino IDE (or Raspberry Pi OS + Thonny/Python). 2. Wire simple LED blink on pin 13 (or GPIO). Upload/test code. Celebrate first win! 3. Open 37-in-1 kit. Pick DHT22 or PIR. Wire it (3-4 pins typical: VCC, GND, Signal). Use library examples. 4. Log data to Serial Monitor (Arduino) or file (Pi). Note readings. 5. Document: Take photos of wiring, save code snippets in this sheet or MKDocs. Resources: Arduino.cc tutorials, kit PDF/videos, Adafruit learn guides for sensors. Blockers to watch: Wrong voltage (most 5V or 3.3V - check!), loose wires, library install.
PHASE 2: AUTONOMIC CORE (Week 2 - Biometrics Live)
Steps: 1. Wire MAX30102 (I2C: SDA/SCL + VCC/GND). Use SparkFun or Adafruit library. Get HR & SpO2. 2. Add GSR module. Calibrate on your skin (resting vs. after activity). Log changes. 3. DHT22 for temp. Compare body vs ambient. 4. Combine: Simple sketch that prints all three to Serial + timestamp. 5. Optional: Plot in Serial Plotter or export to CSV for Excel analysis. Tip: Start with one sensor at a time. Use pull-up resistors on I2C if needed (4.7k typical).
PHASE 3: TACTILE & MOTION (Week 3 - E-Skin Feel)
Steps: 1. Wire single FSR with 10k resistor (voltage divider). Read analog value, map to 0-100 'pressure'. 2. Add 2-4 FSRs in array. Print all values. Simple 'touch map'. 3. MPU6050: I2C, get accel/gyro data. Detect tap or tilt. 4. Combine: When pressure detected + motion, trigger LED or serial message 'Contact!'. 5. Stretch goal: Simple threshold for 'nervous system alert' (e.g. sudden pressure = high priority).
PHASE 4: WIRELESS & POWER (Week 3-4 - Mobile Node)
Steps: 1. ESP32 setup: Blink, connect to WiFi, send simple HTTP or MQTT message. 2. Integrate previous sensors to ESP32 (many have good libraries). 3. Battery: Wire LiPo + charger. Test runtime. Add deep sleep for power saving. 4. Data flow: ESP32 → local Python script on PC/Pi that logs to CSV or your MKDocs. 5. Test portable: Carry node around job site or home, log 'autonomic' data (your stress/motion during day).
PHASE 5: INTEGRATION & LORE (Ongoing - Make it Yours)
Ideas: - Feed sensor data into simple Python script that generates 'soul essence' readings or environmental lore fragments for Travelers. - Use in game dev: Real sensor input controls virtual character state (Ani Void 'feeling' the world). - Personal: Biofeedback for electrician work - track HRV during physical tasks, correlate with fatigue. - Next hardware: Add more FSRs for full 'skin' patch, or explore cheap EEG/EMG modules later. - Document everything in your Living Lore Bible (MKDocs) - wiring diagrams, code, photos, reflections. Remember: This is your nervous system for the universe you're building. Keep learning, keep building.

## Component_Specs
📋 COMPONENT SPECS, PINOUTS & QUICK START CODE
Component | Function | Interface | Wiring Notes | Quick Code Approach | Tips / Common Issues
MAX30102 | Pulse/HR/SpO2 | I2C (SDA/SCL) | VCC=5V/3.3V, GND, SDA, SCL. Optional INT pin. | Use SparkFun MAX3010x library. Example: read Red/IR values → calculate BPM & SpO2. Serial print. | Start with library example 'Example1_Basic_Readings'
GSR | Skin Conductance | Analog out | VCC, GND, Signal (A0). Some have digital too. | Read analog value. Higher = more conductance (arousal). Calibrate baseline on your skin at rest. | Simple analogRead + map to 0-100
FSR | Force/Pressure | Analog (needs resistor) | Two pins. Use 10k pull-down resistor for voltage divider on analog pin. | analogRead → map(0,1023,0,100) for % pressure. Multiple FSRs = array. | Adafruit FSR tutorial excellent
MPU6050 | Accel + Gyro | I2C | VCC, GND, SDA, SCL. AD0 for address if multiple. | Use MPU6050 library or DMP. Get ax,ay,az, gx,gy,gz. Detect motion thresholds. | Jeff Rowberg I2Cdevlib popular
DHT22 | Temp + Humidity | Digital 1-wire | VCC, GND, Data. 4.7k pull-up on data recommended. | DHT library. readTemperature(), readHumidity(). Slow (2s interval). | Simple and reliable
ESP32 | WiFi/BT MCU | Many GPIO + I2C/SPI | 3.3V logic! Use level shifters if mixing with 5V Arduino sensors. | Arduino IDE + ESP32 board package. WiFi.begin, HTTPClient or AsyncWebServer. | Great for standalone wireless nodes

## Resources_NextSteps
📚 RESOURCES, LINKS & NEXT STEPS
RECOMMENDED LEARNING RESOURCES
Topic | Where to Find | Notes
Arduino Basics | arduino.cc/en/Tutorial | Official getting started + examples
37-in-1 Kit Tutorials | Search 'KEYESTUDIO 37 in 1' on YouTube | Many video walkthroughs
MAX30102 | SparkFun or Adafruit MAX3010x guide | Excellent libraries and examples
FSR / E-Skin Ideas | Adafruit FSR tutorial + KOBAKANT textile sensors | Inspiration for flexible skin
ESP32 WiFi | Random Nerd Tutorials ESP32 | Best practical WiFi/MQTT guides
I2C Wiring Tips | Adafruit I2C guide | Pull-ups, addressing, troubleshooting
Travelers Lore Tie-in | Your brainstainddev.com/travelers + MKDocs Living Lore Bible | Integrate sensor data into world-building
NEXT STEPS AFTER THIS SPREADSHEET
1. Review Shopping_List tab. Mark priorities, adjust quantities if needed. Start ordering Phase 1 items this week. 2. Set up your workspace: Clear bench space, good lighting, multimeter handy (as electrician you have this!). 3. Install Arduino IDE + libraries for first sensors (DHT, MAX3010x). 4. Update Dashboard milestones as you complete them. Celebrate small wins - they compound. 5. When data is flowing: Think about visualization (Serial Plotter → Python matplotlib → web dashboard later). 6. Lore integration: What does 'autonomic sensing' mean for Ani Void or Teller's world? Jot ideas in Notes column. 7. Share progress on X or with Jojo/son if it feels right - accountability + joy. You're building something real that bridges your physical work skills with the cosmic creative fire. This platform can literally become part of the Travelers universe. Let's make it breathe.
SAFETY & PRACTICAL NOTES (Electrician Apprentice Edition)
• All these sensors are low-voltage (3.3V-5V). Safe, but still respect polarity and don't short power rails.
• On job sites: Protect boards from dust, sparks, moisture. Use project boxes or bags when transporting.
• Vision: Good lighting + magnification if needed for small pins. Your aging eyes deserve it.
• Power: Use proper USB or regulated supplies. LiPo charging - follow module instructions to avoid fire risk.
• Fun first: If something doesn't work immediately, debug one wire at a time. The learning is the point.